## Sheet1
No | Content | PIC | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
|  |  | 2022-02-10 | 2022-02-11 | 2022-02-12 | 2022-02-13 | 2022-02-14 | 2022-02-15 | 2022-02-16 | 2022-02-17 | 2022-02-18 | 2022-02-19 | 2022-02-20 | 2022-02-21 | 2022-02-22 | 2022-02-23 | 2022-02-24 | 2022-02-25 | 2022-02-26
1 | Introduction
1.1 | Finding info on wnv in USA | Zhe Wei | bar: 2022-02-10 to 2022-02-12
1.2 | Find info on wnv in Chicago, Illinois | Zhe Wei | bar: 2022-02-10 to 2022-02-12
2 | Problem Statement
2.1 | Crafting problem statement | Cheng Yeow | bar: 2022-02-12 to 2022-02-13
2.2 | Measure of success | Cheng Yeow | bar: 2022-02-23 to 2022-02-24
3 | EDA
3.1 | Train | Vincent / Zhe Wei | bar: 2022-02-12 to 2022-02-15
3.2 | Weather | Zhe Wei | bar: 2022-02-14 to 2022-02-16
3.3 | Spray | Vincent | bar: 2022-02-14 to 2022-02-16
3.4 | Test | Vincent | bar: 2022-02-16 to 2022-02-17
4 | Data Cleaning
4.1 | Weather | Zhe Wei | bar: 2022-02-15 to 2022-02-16
4.2 | Spray | Vincent | bar: 2022-02-15 to 2022-02-16
5 | Feature Engineering | Vincent / Cheng Yeow | bar: 2022-02-17 to 2022-02-19
6 | Modelling
6.1 | Model Selection | Cheng Kiat | bar: 2022-02-20
6.2 | Optimization | Cheng Kiat | bar: 2022-02-21
6.3 | Model Evaluation | Cheng Kiat | bar: 2022-02-22
6.4 | Feature Importance | Cheng Kiat | bar: 2022-02-22 to 2022-02-23
6.5 | Kaggle Score | Cheng Kiat | bar: 2022-02-23
7 | Cost Benefit Analysis
7.1 | Find cost of pesticide | Zhe Wei | bar: 2022-02-18
7.2 | Find cost to individual wnv patients | Zhe Wei | bar: 2022-02-18 to 2022-02-19
7.3 | Pest control worker wage | Zhe Wei | bar: 2022-02-20
7.4 | Cost Benefit Strategy and Calculation | Zhe Wei | bar: 2022-02-18 to 2022-02-22
8 | Conclusion abd Recommendations | May Gee | bar: 2022-02-23 to 2022-02-24
9 | Readme | All | bar: 2022-02-23 to 2022-02-25
10 | Presentation | All | bar: 2022-02-23 to 2022-02-25
| Kaggle repository for Group work | https://www.kaggle.com/chengkiattan/ga-project-4-1/